## Slide 1
Core Risk Platform — Programme Org-on-a-Page
Peak ~105 FTE · 18–24 month delivery · Three risk domains · 20+ integrations · Full UI suite
PEAK
~105 FTE
LEADERSHIP
13 FTE
Programme-long
PROGRAMME & DELIVERY
• Programme Director • Programme Manager • Delivery Manager
ARCHITECTURE & ENGINEERING
• Chief Architect • Lead Solution Architect • Domain Architects (Data · Risk · UI) • Head of Engineering
PRODUCT, RISK & PMO
• Head of Product • Risk & Compliance Lead • Model Risk Lead (SR 11-7 / SS1/23) • PMO Analysts × 2
CORE
CAPABILITIES
45 FTE
Build the platform.
Serve every team.
Cloud Platform & SRE
EKS · Terraform · OTel · ArgoCD
7 FTE
Data Platform
Iceberg · Spark · Flink · dbt · DQ
8 FTE
Integration & Messaging
Solace · Kafka · FIX · SWIFT · adapters
7 FTE
UI Platform
Design system · shell · auth
6 FTE
Orchestration & Workflow
Temporal · Drools · Airflow
6 FTE
Quant Library
QuantLib · curves · Ray · scenarios
5 FTE
Identity, Sec & Gov
IdP · Vault · RBAC · audit · lineage
6 FTE
FEATURE
TEAMS
51 FTE
Own a domain
end-to-end.
Credit Risk
Phase 1
EAD · PFE · CVA · limits
1 EM · 1 Tech Lead · 3 Backend
1–2 Quant Dev · 2 Frontend
1 PO · 1 Risk SME · 1 BA · 1 QA
12 FTE
Market Risk
Phase 2
VaR · ES · sensitivities
1 EM · 1 Tech Lead · 3 Backend
1–2 Quant Dev · 2 Frontend
1 PO · 1 Risk SME · 1 BA · 1 QA
12 FTE
Liquidity / CCH
Phase 3
IM/VM · LCR · 5–8 CCHs
1 EM · 1 Tech Lead · 3 Backend
1–2 Quant Dev · 2 Frontend
1 PO · 1 Risk SME · 1 BA · 1 QA
12 FTE
Risk Reporting
Cross-domain
Self-serve · MiFID/EMIR/FCA · EUDA decom
10 FTE
Test Engineering
Programme-wide
Framework · NFR · perf · automation
5 FTE
PHASE
RAMP
FTE by phase
30
P0 · M0–3
Mobilise
70
P1 · M3–9
Foundation + Credit
100
P2 · M9–15
+ Market Risk
105
P3 · M15–21
+ Liquidity / CCH
60
P4 · M21–24+
Stabilise / BAU
Steady-state run-the-bank ~50–60 FTE, distributed across the same team shapes at reduced scale.